Oliver Fire Complex Information Update

### Tuesday, June 24, – 9:00 am

#### Sierra National Forest

Madera Mariposa Ranger Unit

_______________________________________________________

Headlines:

The Oliver Complex is comprised of numerous lightning fires burning in the Sierra National Forest north and west of Oakhurst.  The fires of greatest concern are the Oliver Fire in the Ponderosa Basin, Silver Knob Fire, north of Ahwahnee and the Westfall Fire burning south of Fish Camp.   Yesterday, winds were light; fire behavior was moderate, allowing fire fighters to make good progress on all fires.

| Fire Status Acres Burned: 1,292 total of all fires Oliver Fire, 1000 acres Silver Knob Fire 400 acres Westfall Fire 50 acres Chiquito Fire 10 acres Star Fire 30 acres Gagg, Poison and 7 other fires contained Percent Contained: Oliver Fire 0 percent Silver Knob 10 percent Westfall 50 percent Chiquito 50 percent Star Fire 0 percent | Expected Containment: Monday June 30th Injuries: none reported Structures Threatened: 150 Ponderosa Basin Structures Destroyed: None reported Resources Crews: 11 Engines: 50 Helicopters: 2 Air Tankers: 2 Air Attack: 1 Dozers: 8 Total Personnel Assigned: 400 |
| --- | --- |

Fire Situation:

Excellent progress has been made on multiple lightning-caused fires.  Four lightning fires have been contained and are in the mop up stages.   The Oliver Fire, burning near Ponderosa Basin, is about 1,000 acres.  Yesterday, winds were light and firefighters made good progress constructing dozer line on the Chowchilla and Aurora Roads, with direct hand line constructed along the Standard Mill Road.  Fire engines are staged in Ponderosa Basin for structure protection.  On the Silver Knob Fire north of Ahwahnee, good progress was made securing a fire line using the Miami Mountain Road on the south, Forest Road 6S63 on the east and Forest Road 5S12 on the west.  The Westfall Fire, burning south of Fish camp has indirect line around the fires edge and fire fighters are executing a slow burn to assist in containment.

Evacuations:

The Mariposa County Sheriff’s Office has made pre-evacuation notifications to residents living on the dirt portion of Chowchilla Mountain Road starting at the 5600 Block and continuing up the mountain to and including the 6100 block of Chowchilla Mountain Road.  This includes Varden Ct and Arora Ct intersecting with Chowchilla Mountain Road. Residents need to be alert to changing conditions.

Road and Area Closures

All roads and trails are open with the exception of Chowchilla Mountain Road which is open to residents only.  Chowchilla Mountain Road from Wawona to Ponderosa Basin is closed.

Health Advisories

Early morning drift smoke will settle in the Oakhurst, Ahwahnee Areas.  During the duration of the smoke conditions:

- Persons with asthma or other respiratory problems should avoid outdoor activities.

- All persons should avoid strenuous outdoor exercise.

- Anyone experiencing health problems related to the air quality should contact their primary care physician.

Fire Information:

Sierra National Forest, North Fork Office at 559-877-2218   Hours:  7am – 10pm

Cal Fire –Madera Mariposa Ranger Unit, Mariposa at 209-966-4784   Hours:  8am -8pm

Sierra National Forest Website:   www.fs.fed.us/r5/sierra